## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1919 | Simulate a 30 audio car sales journey to analyze the Falcon S2 buying process. | MUST HAVE | 5 | Avidi Sneha Sanjana | 3- Completed
2 | 2 | 1919 | Converted 30 audio sales journey into text format | MUST HAVE | 4 | Avidi Sneha Sanjana | 3- Completed
3 | 3 | 1919 | Conversion of live speech recording to text format | MUST HAVE | 5 | Avidi Sneha Sanjana | 3- Completed
4 | 4 | 1919 | Identification of only customer sentences from the audio file and analyze the sentiment,intent and entite's for each customer sentence in the conversation | MUST HAVE | 5 | Avidi Sneha Sanjana | 3- Completed
5 | 5 | 1919 | Analysing the sentiment, intent and entites along with ai sugesstiond for each customer sentence from the audio file and as well as the recording. | MUST HAVE | 4 | Avidi Sneha Sanjana | 3- Completed
Note on F1: ====== ID#AAABtSAQqZ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1919 | 1362 | Collection of 30 datasets & text conversion | 2025-10-16 | 2025-11-04 | Avidi Sneha Sanjana | Build | 3- Completed | 10
1919 | 1362 | Conversion of live speech to text | 2025-11-12 | 2025-11-22 | Avidi Sneha Sanjana | Coding | 3- Completed | 8
1919 | 1362 | Sentiment analysis for the customer sentences of audio files and as well as live speech | 2025-11-25 | 2025-12-02 | Avidi Sneha Sanjana | Integration Test | 3- Completed | 8
1919 | 1362 | AI suggestions for the live speech customer sentences | 2025-12-06 | 2025-12-11 | Avidi Sneha Sanjana | Integration Test | 3- Completed | 11
Note on D2: ====== ID#AAABtSAQqaA Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABtSAQqak Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABtSAQqaI Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABtSAQqaU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABtSAQqaY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABtSAQqac Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABtSAQqbA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABtSAQqaE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABtSAQqa0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABtSAQqag Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABtSAQqas Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABtSAQqaM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABtSAQqao Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABtSAQqa8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABtSAQqaw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABtSAQqa4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABtSAQqaQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
M-1 | 2025-11-04 | Presented Milestone1 tasks | Started filling form today
M-2 | 2025-11-12 | Understand the process of implementing milestone2 | Started working on milestone2
M-2 | 2025-11-13 | Installing the software that are required for the task | working on it
M-2 | 2025-11-17 | Implementing the code for the milestone2 | Implemented
M-2 | 2025-11-19 | Identified Errors | Working of bugs
M-2 | 2025-11-20 | Completed the task | Rectified the bugs
M-2 | 2025-11-25 | Presented Milestone2 | Updated all the agile documents
M-3 | 2025-11-25 | Undestand how to work on milestone3 | Started implimenting
M-3 | 2025-11-26 | Developing the code for milestone3 | work in progress
M-3 | 2025-12-27 | Dicussed about the output | Tried to modify the functionality
M-3 | 2025-12-01 | Presented the milestone3 | Updated all the sheets
M-4 | 2025-12-07 | Discussed about the task of milestone4 | Started working on it
M-4 | 2025-12-10 | Presented the milestone4

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-11-04 | Avidi Sneha Sanjana |  | Yes
2 | 2 | 2025-11-12 | 2025-11-22 | Avidi Sneha Sanjana |  | Yes
3 | 3 | 2025-11-25 | 2025-12-02 | Avidi Sneha Sanjana |  | Yes
4 | 4 | 2025-12-06 | 2025-12-11 | Avidi Sneha Sanjana |  | Yes